## Task
Task | Assignee | Status | Target Date
Item Excel Import | Lester | On-going | 2018-10-29
Document Series reset settings | Angelo | Pending | 2018-10-29
Integrate Item Import to BOQ | Lester | Pending | 2018-10-30
Integrate Item Import to BOM | Lester | Pending | 2018-10-30
Project Change Request Module | Joseph | Pending | 2018-10-29
Create Module | Joseph | Done
Only PCR can only be created when an SEF has an Active SO. | Joseph | Pending | 2018-10-29
Active Items (No slow moving items: 2years unmoving) | Joseph | Pending | 2018-10-29
One is to one replacement Of Item | Joseph | Pending | 2018-10-29
If Approved, It will item selected at PCR will effect change of SO items | Joseph | On Progress | 2018-10-29