## Daily Tracking
Date | Project | Module | Sub Module | Description | Start Time | End Time | Remarks
2018-02-12 | Sunrise | Call Logs |  | Additional Call Topic | 8:30 | 9:00
2018-02-12 | Sunrise | Call Logs |  | Update of Call Log changes to System and Report | 9:00 | 12:00
2018-02-12 | IAMS | Replenishment |  | Replenishment report 2 update computation / Acct Entries | 13:00 | 14:00
2018-02-12 | Petronell | Depository |  | Unit Cost for detail instead of SP | 14:00 | 14:30
2018-02-12 | Petronell | Customer |  | Credit Limit Add Balance - Add SQL Function,View etc | 14:30 | 16:00
2018-02-12 | IAMS | Replenishment |  | Acct Entries For VP status / Testing | 17:00 | 20:00
2018-02-13 | IAMS | Replenishment |  | For VP status module process and script | 8:45 | 9:00
2018-02-13 | IAMS | Cash Advance |  | CA Already release but still approve status. Double approve bug. Added new validation script upon approve | 9:00 | 10:20
2018-02-13 | IAMS | Cash Advance / Liquidation |  | Added status validation script upon save | 10:20 | 10:40
2018-02-13 | IAMS | Cash Advance / Liquidation |  | Testing | 10:40 | 11:00
2018-02-13 | Petronell | Collection Monitoring |  | Rename - PDC to Collection, Add Clear & Bounce function | 13:00 | 13:30
2018-02-13 | Petronell | Payment Transaction |  | Rename - Bank Transfer to Bank Deposit, include to Collection Monitoring with same as check payment | 13:30 | 14:00
2018-02-13 | Petronell | Cash Turn Over |  | New Module | 14:00 | 14:45
2018-02-13 | IAMS | Replenishment |  | Acct Entries not balance | 14:45 | 16:00
2018-02-13 | Petronell | Fuel Transfer |  | New Module | 17:00 | 18:00
2018-02-14 | IAMS | Replenishment |  | Acct Entries not balance | 8:30 | 10:00
2018-02-14 | IAMS - EPP | EPP - Invoice |  | Address not correct/Report/Delivery Address at SO and DR details | 10:00 | 12:00
2018-02-14 | Petronell | Fuel Transfer |  | New Module/ Depository Balance browsing & movement / Approval / Cancel / Add Item | 13:00 | 18:00
2018-02-15 | Petronell | Fuel Transfer |  | Listview setup/format | 8:30 | 9:30
2018-02-15 | Sunrise | Call Logs |  | Additional Call Topic/Call Topic1/Resolution | 9:30 | 10:00
2018-02-15 | Sunrise | TCP Socket |  | Discussion with Mr Joseph Sy through viber about communication to TCP on there inventory system | 10:00 | 11:00
2018-02-15 | Petronell | Cash Turn Over |  | Shift field/ Employee field browsing | 11:00 | 11:30
2018-02-15 | Petronell | Customer |  | New Field Outstanding Balance / Computation / Sequence | 11:30 | 11:45
2018-02-15 | Petronell | Cash Turn Over |  | Listview setup/format | 11:45 | 12:00
2018-02-15 | Sunrise | TCP Socket |  | Testing of TCP Requesting | 13:00 | 14:00
2018-02-15 | IAMS | Petty Cash Fund |  | Script for Backdooring LIQUI AND CA that are manually replenished | 17:00 | 17:30
2018-02-19 | Petronell | Fuel Transfer |  | Validation not showing/ add new validation for quantity | 8:30 | 9:30
2018-02-19 | Sunrise | TCP Socket |  | Testing of TCP Requesting Customer Order Seach | 9:30 | 10:30
2018-02-19 | Petronell | Fuel Transfer |  | put depository on add item/ add validation only 1 per depository | 10:30 | 11:30
2018-02-19 | Petronell | Sales Invoice |  | Incorrect description item name / wrong spelling "Trasaction" | 11:30 | 12:00
2018-02-19 | IAMS | Cash Advance / Liquidation |  | Incorrect trasaction status | 13:00 | 14:00
2018-02-19 | IAMS | Purchase Order |  | Wrong Payment History Amount | 14:00 | 14:30
2018-02-19 | Sunrise | TCP Socket |  | Testing of TCP Requesting Customer Order Message/Status | 14:30 | 18:00
2018-02-20 | IAMS | Cash Advance |  | Wrong click receive - backdoor | 8:45 | 9:00
2018-02-20 | Sunrise | TCP Socket |  | TCP Socket development/tables/formats | 9:00 | 10:30
2018-02-20 | Petronell | Login |  | pPOSShiftlogin - script changes/update | 10:30 | 10:40
2018-02-20 | Petronell | Cash Turn Over |  | record ID 1 not showing/ bug control / from dxListview to SelectBox | 10:40 | 10:50
2018-02-20 | Sunrise | TCP Socket |  | TCP Socket development/tables/formats | 10:50 | 12:00
2018-02-20 | IAMS | RELEASED PACKAGE |  | Update Scipt/Package | 13:00 | 18:00
2018-02-21 | IAMS | Replenishment |  | Acct Entries | 8:30 | 9:00
2018-02-21 | IAMS | Release Application |  | New software for update | 9:00 | 16:00
2018-02-22 | Sick Leave
2018-02-23 | IAMS | Sales Order |  | PCR-2018022120- SO Account Transfer | 8:30 | 9:00
2018-02-26 | IAMS | Replenishment |  | PCR-2018022121- New Detailed Tab And Acct Entry | 9:00 | 18:00
2018-02-27 | IAMS | Replenishment |  | PCR-2018022121- New Detailed Tab And Acct Entry | 9:00 | 12:00
2018-02-27 | IAMS | Sales Opportunity |  | Validation for SRP | 13:00 | 13:30
2018-02-27 | IAMS | Liquidation |  | Wrong Status | 13:30 | 14:30
2018-02-27 | IAMS | Replenishment |  | PCR-2018022121- New Detailed Tab And Acct Entry /// Testing | 14:30 | 20:00
2018-02-28 | IAMS | Replenishment |  | Missing Expense entry | 9:00 | 18:00
2018-03-01 | Sunrise |  |  | Viber Call - Meeting with Mr. Josep Sy - about sunrise revamp/redevelopment | 8:30 | 10:00
2018-03-01 | IAMS | Replenishment |  | Summary detail per type - change to Summary per transaction only | 10:00 | 15:00
2018-03-01 | Sunrise | Quickbooks/Uploader |  | Error uploading to quickbooks - added try catch in other codes | 15:00 | 18:00
2018-03-02 | IAMS | Item |  | Scripting/Generate report to excel | 9:00 | 10:00
2018-03-02 | Sunrise | Call Logs |  | New Call Status Field / Validation Adjustment RA Number | 10:00 | 13:00
2018-03-02 | Sunrise | Call Logs By Item # Report |  | Call Status Field / Column Adjustments | 13:00 | 14:00
2018-03-02 | IAMS | Sales Endorsement |  | BFRD / Payment Terms Computation | 14:00 | 18:00
2018-03-05 | Sunrise | Call Logs |  | Field Position / UI | 9:00 | 10:00
2018-03-05 | IAMS | Sales Endorsement |  | BFRD / Fields adjustments | 10:00 | 11:00
2018-03-05 | IAMS | Replenishment |  | Validation for Approve Cost/ Accounting Entries for VP Scenario | 11:00 | 18:00
2018-03-06 | Sunrise | Call Logs |  | Call Status validation | 8:00 | 8:30
2018-03-06 | Sunrise | Report |  | Return Authorization error/ SQL Conversion error | 8:30 | 10:00
2018-03-06 | IAMS | Opportunity |  | BFRD | 10:00 | 15:00
2018-03-06 | IAMS | Sales Endorsement |  | BFRD | 15:00 | 18:00
2018-03-06 | IAMS | Petty Cash Custodian |  | Account transfer - Modeo to Rizza | 18:00 | 19:00
2018-03-07 | IAMS | Sales Endorsement |  | BFRD | 8:00 | 10:00
2018-03-07 | IAMS | RELEASED PACKAGE |  | Replenishment | 10:00 | 10:00

## Plan for next week
Project | Module | Sub Module | Description
Sunrise | TCP Socket |  | Development of tcp communication between transactions of Insys Sunrise and CODIS System
IAMS | Petty Cash Fund(All module) |  | Updating/Testing/Correction of Accounting Entries and System flow for deployment