## Sheet1
Date of OT | Time | Developer/PM | Target | Accomplishments | Next Step | Timeline
2018-05-11 | 6PM - 8PM | Nharei | Preparation of items for UAT and testing of Sales Pipeline new modules | Review of Redmine PPT for User Training Redmine User Manual Review Testing of Sales Pipeline new modules | for discussion to the team
2018-05-11 | 6PM - 8PM | Barbs | Testing of Leads to Sales Endorsement v.2.1.2.7 | Testing of Leads to Sales Endorsement listed on Redmine | continue testing on Monday
2018-05-11 | 6PM - 8PM | Julius | Development and testing of approver matrix | Development and Testing of Approver Matrix Support during our testing Testing of Opportunity Discount | Fixing of issued items at redmine (Opportunity
2018-05-11 | 6PM - 8PM | Jefrey | Checking of UI modifications and review of Redmine for development | Review of issues at red mine and checking if the modifications is applicable Assigning of issues to developer | Development of redmine issues
2018-05-11 | 6PM - 8PM | Lester | Development of Import feature at Leads module Fixing of issues at Redmine for Leads to Client | Development of Import feature at Leads module and testing if the modification will be applicable | Testing of importing of Leads
2018-05-11 | 6PM - 8PM | Brien | Testing of IMF Request to Accounts Receivable Creating of test scripts for Accounting | Testing of IMF Request to Sales Order Creating of test scripts for Accounting | testing of Sales Order to Accounts Receivable
2018-05-11 | 6PM - 8PM | Arnie | Review of the test scripts for Accounting Testing of Accounting entries for AP, AR and INV | Testing of Accounting entries for AP and Inventory | Testing of Accounting entries for AR and Inventory